Shelter/NFI Cluster Coordination Meeting, Dahuk

**Location:** BRHA conference room, Dahuk

**Date and time:** 11.15am,9th May 2017

**Attendance:** ACTED, BRHA, CARE, CRS, Dorcas, DRC, FRC, GRC, ICRC, IRC, IOM, Medair, Mission East, NRC, Reach, Tearfund, PWJ, Qandil, UNHCR, UNOCHA,

|  |  |  |
| --- | --- | --- |
| Agenda Item | Key Points | Actions |
| Zone North Camps | * Gaps: Clothing and bread ovens in Nargzilia IDP camp.
* GRC in discussion with UNHCR about need for multipurpose cash (MPCA) in Nargzilia.
* Summerization in Nargziila – including construction of shaded areas (potentially using shelter kits) and water coolers. UNHCR in discussion with CRS re camps in South. IOM also working in camps in south. GRC ready to provide summarization.
* Hamam Al Alil continues to fill up with IDPs from W Mosul. Haji Ali is now full.
* Gaps for Cooking stoves and gas stoves in Qaymawa (but no IDPs present). No IDPs yet in Amalla IDP camp currently. Only 20 new individuals this week in Nargzilia.
 | * Any agencies with capacity/funding to respond to contact Tearfund or S-NFI cluster.
* Shada to convene meeting with S-NFI cluster, CWG, UNHCR, GRC and BRHA to decide way forward –provisional date Tuesday 16th May. Any other partners interested in MPCA response in Nargzilia to notify CWG or S-NFI cluster.
 |
| Newly retaken areas and out of camp response | * Qawsiyat update: Medair completed NFI and BSK distributions by Medair and Dorcas complete. DRC also distributed items.
* Alamuk & Janek: Ongoing interventions. Check Newly Retaken Areas Skype group for details of distributions.

Planned Assessments/Distributions:* Dorcas – joint shelter assessment in Khorsabat with ACTED planned
* Medair – Assessment in Sheikh Mohammed W of Qawsiyat postponed to next week
* CRS – camp/non camp in Hamam Ali and Qayarrah planned but bridge closed.
* Mission East NFI distribution in Bashiqa
* WHH – Education assessment in Telskuf
 | * Partners to get in touch with S-NFI cluster if interested in working in Alamuk, Janek, surrounding towns, and Shindukhah and Sahlej.
 |
| Funding Update | * ECHO – closing a round of funding shortly with a second round expected later this year
* OFDA – closing a round of funding shortly with expected decline from September
* DFID – not funding shelter at this point
* German group – 7m Euros available for NGOs
* Embassies - unknown
 |  |
| Key updates by partners | * ACTED – Shifting to towns of Mosul. Prog Manager in Erbil.
* New Dorcas Prog Manager for S-NFIs and Food – Rachel Thompson
* Security incidents – none to report.
* ME – security assessment in Badush – before fighting started other side of river. Sheikh Mohammed is a volatile area to work in. Locals receptive. ISF have reservations about IDPs returning to area from screening site; mustering point nearby, transfer via Hamam Aliel. Hard to operate in near future.
 | * Partners to identify any gaps form funding changes to S-NFI cluster.
 |
| Update from national level | * $5m to 9 partners. Technical review in GMS. Funding dispersed by June if everything goes to plan.
* Base shelter assessment – To be Discussed in national meeting; Already shared yesterday via mailing list. Format/Qs to be released early next week. Good partner demand from previous meeting in Erbil; UN HABITAT – no current planned work but part of meeting; UNHCR began 3,000HHS assessments on shelter vulnerability.
 | * Coordination between format of shelter assessment and planned ACTED shelter assessment in Khorsabad
 |
| Distribution to undocumented IDPs out of camps | * National Cluster guidelines for distribution forthcoming.
 | * Laurence to consolidate the experiences shared and put them in the distribution guidelines (ongoing)
 |
| AOB | * UNHCR - Nargzlia and Qaymawa tents to be redeployed to other locations as required.
* Suggestion from BRHA that Air Coolers are a high priority for seasonal assistance in Nargzilia IDP camp.
* UNHCR/PWJ Domiz shelter assessment presented.
 | * BRHA to investigate option for best use of tent not currently occupied or those that require minor repair.
* Presentation to be reviewed by BRHA and distributed.
 |

**Next meeting:** Tuesday 23rd May, 11am at BRHA Conference Room

**Minute rotation:** Completed – UNHCR, ACTED, PIN, Tearfund.

 Upcoming… WHH (next meeting) then CARE