**PUNTLAND (GAROWE) EMERGENCY SHELTER/NFI CLUSTER MEETING MINUTES**

**Venue:** NRC conference room, Garowe

**Chair:** Chairman Regional shelter cluster coordinator: Abdihakim Mohamed

**Participants**

|  |  |  |  |
| --- | --- | --- | --- |
| **S/No** | **Name of the Particpants** | **Organization** | **Email** |
| 1 | Mohamoud Saeed | UNOCHA | [saeednooh@un.org](mailto:saeednooh@un.org) |
| 2 | Abdihakim Mohamed | NRC | Abdihakim.mohamed@nrc.no |
| 3 | Nadeem Ilyas | NRC | nadeem.ilyas@nrc.no |
| 4 | Eng. Mohamud Hassam | UNHabitat | mxasan3@hotmail.com |
| 5 | Hassan Camale | Horda local NGO | Hassan.camalle@gmail.com |
| 6 | Mohamed Salah | UNHCR | 'Mohamed Salah (salah@unhcr.org)' |
| 6 | Omar Shiekh | Kaalo Local NGO | [omarshiikh001@gmail.com](mailto:omarshiikh001@gmail.com) |
| 7 | Saida Nuur | NRC ICLA | [Saida.nur@nrc.no](mailto:Saida.nur@nrc.no) |
| 8 | Hamdi Abdulahi | Care International | [hamdi.abdullahi@care.org](mailto:hamdi.abdullahi@care.org) |
| 9 | Ahmed Isse | NRC | [Ahmed.omar@nrc.no](mailto:Ahmed.omar@nrc.no) |

**Agenda**

* 1.       Review of previous meeting minutes and action points.  
  2.       Update of ongoing construction of 100 permanent shelters in Jilab two  
  3.       Distribution of NFI kits to drought effected people  
  4.       Durable solution for the shelter/NFI projects   
  5.       Information of the new displacement in Nugal region  
  6.       AOB

**Opening Remarks**

The meeting began with welcome and quick round introduction by the participants and review of the action points of previous meeting minutes.

1. **Update of completed construction of 100 permanent shelters in Jilab two**

The Norwegian Refugee Council (NRC) has received funds from “United Nations High Commissioner for Refugees” UNHCR to implement permanent shelter project to locally Integrating IDPs and vulnerable host community in Garowe, Puntland, Somalia which includes as main activities; construction of 100 permanent shelters, 100 family latrines, 1 community center and other components.

NRC has shared with shelter cluster partners that it has completed 100% construction of 100 permanent shelter with family latrines, and community center.

Cluster coordinator at Nugal region and NRC managers as well as cluster partners visited the field in Jilab 2, the site in which NRC construction of 100 permanent shelter, Family latrines and 1 community center is going on and feedback of the cluster members was that they are very happy with the ongoing construction of shelter but cluster members’ noted the following gaps

1. The new permanent site needs health post as people occupying the shelters are most of them women and some of them are pregnant and need health care in their time of delivery.

So it is important that people to receive health care so cluster members requested all the agencies working in the health sector to deal with this matter.

1. Cluster members noted that the new permanent shelters have no water and NRC has requested from UNHCR to look for fund for water extension and solar lumps which UNHCR promised that they will look in to it.
2. The new permanent site “Jilab 2” has no schools and beneficiaries shared cluster members that their children need schools but NRC and UN habitat mentioned that the site plan they have developed includes school and other spaces for future buildings
   * **Action point**

* **Shelter cluster coordinator will share the above gaps with other partners and cluster partners’ officials will share this information with their seniors.**

1. **Distribution of NFI kits to drought effected people**

* UNHCR shared that there is planned distribution of 300 NFI kits to Usgoray village under Dangorayo and most of people living in Dangorayo village are the drought effected people and erected buuls outside the villages and as shared with us UNHCR people need emergency NFI and shelter kits.

Cluster members noted that there is some villages already occupied by number of IDPs those need emergency NFI distribution but there is no any agency that has NFI except UNHCR which has 5000 NFI’s.

* 1. **Action point**
* **UNHCR will start distribution of NFI kits to those people effected drought in Usgoray and other villages under Dangorayo.**

1. **Durable solution for Nugal IDP**

* Durable solution projects have already started as the construction of 100 permanent shelter has started in Garowe but there is gaps in other areas of the other activities of the durable solution and cluster member noted those people moved to Jilab 2, need projects relating to livelihood, water and sanitation, education and health facilities.
* There is also unused space of the already available land which approximately 430 new shelters can be constructed with all necessary facilities.

1. **Action point**

* **Cluster members agreed that most of DPs living in Jawle need durable solution projects with includes all other sectors.**

1. **Information of the new displacement in Nugal region**

* The local authority shared number of villages displace people have already reached and also expectancy of other people those lost their livestock in the current drought and all those people will need emergency distribution of livelihood, NFI, Shelter kits and so on.

1. **AOB**
   1. **Action point**

* **Local authority will submit the exact number of HHs those displaced from their inhabitance as result of the drought.**

END.